## Checklist
VOSS EVENT MATRIX |  | VOSS EVENT MATRIX
Event Name: Wrestle 4 Hope
DATE & TIME: 06/15/2025
COST: $300
SPEAKER: N/A
THEME: Gladiators for God
PROJECT MANAGER: TINA PALOMERA
LOGISTICS/OVERSEER: | DETAIL | CONTACT | NOTES
MAN POWER | Set up any chairs & tables for each game booth and for general public
SECURITY | Security will help cover area to prevent any issues, keep order of service
DÉCOR | N/A
BUDGET | Run by Sis Janine, submit check requisitions and deliver checks to those designated. Collect receipts and submit to VOSS Finance Office
SOUND | Sound person set up and tear down.Christian music to play before.
MULTIMEDIA | N/A
PROMOTIONAL MATERIAL | Design Flyer/Promo Video/Print Material for service (agendas, how to give, etc...)
PHOTOGRAPHY/MEDIA | Take photos/video for future events
REGISTRATION | Collect monies and keep tally of number of registrants. Please arrive 2 hours before.
TRUSTEES | Collect and count finances day of. Make sure they are turned into VOSS office; registration and offering. Sister Rachel's Office
DJ/ENTERTAINMENT | Making sure that appropriate Christian Music is downloaded 1 week in advance & all tiktok videos are submitted before December 10th
T-SHIRTS | Collect Sizes/Payments, distribute t-shirts
FOOD TABLE | Schematic and setup of food table, ensure that all families bring a family size appetizer. Have
SERVICE/OVERSEER: | EVENT MC:
AGENDA | Contact Elena Caraveo 1 week before event to have event agenda typed and approved
WORSHIP | Coordinate band, singers, and worhsip setlist
SPECIAL MUSIC/PRESENTATION | Creative and cutting edge. Special ensemble/spoken word and/or skit
PRAYER | Prayer the day of and organize prayer weekend at least 1 week prior to the event.
GREETERS/USHERETTES | Need a team of #______. Arrive 1 hour early day of event. Coordinate team and place them at baskets and front doors. Make sure we have United We Can envelopes.
EVANGELISM/OVERSEERS:
MAPS FOR EVANGELISM | Map out location/split in different directions
TEAM LEADERS | Will be appointed to oversee each evangelism team before service, lead them to locations, make sure everyone is together and returns on time
BULLHORNS/SIGNAGE | Have signs ready and bullhorns
CONNECT CARDS/FLYERS FOR LOCAL CHURCH | For any salvations, cards to be given to P.Jon & Event QR code follow up cards
SECURITY | Security will help cover area to prevent any issues, keep order for rally/event