## In Work
Church Name: Mercy Gate Church - Box Elder |  |  | Location: Box Elder, South Dakota & Ellsworth AFB (Population ~20,000)
Pastor: Andrew (Andy) Daniel |  |  | Affiliation: SBC, BBFI, NAMB, DBC, BHABA
Phone: 417-824-7177 |  |  | Website: mgbe.church
Address: 400 225th Street, Box Elder SD 57719 |  |  | E-Mail: andy@mgbe.church
Mercy Gate Church Box Elder - Active Project List – 13 June 2025
Priority | Location | Cost | Notes | Progress | Point of Contact
1 | Entire Building | 200 | Wire Smoke Alarms Together & Add More | Not Started
1 | Parking Lot | 25000 | Gravel All Driving/Parking Surfaces | In Work | Andy Daniel
1 | Foyer | ? | Handicap Accessible Bathroom | Not Started
1 | Worship Hall East | 25 | Fix Trim and Caulk Windows | Not Started
1 | Worship Hall Exit Doors | 25 | Stickers, "Doors Must ... Unlocked…Occupied" | Not Started
1 | Kitchen | 50 | Install Ice Machine | Not Started | Brad Green
1 | Kid's Bathroom | 250 | Replace Toilet | Not Started | Brad Green
1 | Front Boiler Room | 400 | Install Spirovent on Boiler | Not Started | Brad Green/Tony Dobbs
1 | Front Boiler Room | 600 | Repair/Replace Circulation Pump | Not Started | Brad Green/Tony Dobbs
2 | Exterior | 3000 | Build/Buy Storage Shed | Not Started
2 | Exterior Building | 500 | Crawl Space Covers (2 Covers) | Not Started
2 | Fellowship Hall Stairs | ? | Heavy Duty Handrail - Exterior | Not Started
2 | Attic | - | Insulate Access Point | Not Started
2 | Street Lights (3) | - | Straighten | Not Started | BH Power
2 | Green Shed | 3000 | Add Power to Shed &30 Amp RV Hookup for Trailer | In Progress | Brad Green/BH Energy
2 | Fellowship Hall | 500 | Door Push Bar | Not Started
2 | Worship Hall | 1000 | Door Push Bars | Not Started
2 | Breezeway | 200 | Illuminated Exit Sign across from Janitor's Closet | Not Started
2 | Left of Stage Storage Room | 20 | Replace Light Switch (Occasional Malfunction) | Not Started
2 | Kid's Classrooms | 2000 | Install Carpet in 3 Kid's Classrooms | Not Started
3 | HVAC - Janitor/Trailers | - | Insulate Access Covers - Insulation in Attic | Not Started
3 | HVAC - Ceiling | - | Roll Out Insulation - Stored in Attic | Not Started
3 | Worship Hall | 50 | Tie Ventilation to Extisting Piping | Not Started | Brad Green
3 | Attic | 20 | Duct Tape HVAC Piping Insulation Back On | Not Started
4 | Janitor's Closet | 50 | Inventory Paint and Discard All Paint 5yrs old+ | Not Started
4 | Worship Hall Doors | 50 | Replace Weather Seal | Not Started
4 | Fellowship Hall | 150 | Insulate Stairs Under Trailer / Crawl Space | Not Started
4 | Laundry Room | 50 | Remove P-Trap in Crawl Space | Not Started | Brad Green
4 | Foundation | 31000 | Baptistry Foundation Repair | Not Started
4 | Laundry Room | 100 | Repair Sheet Rock | Not Started
4 | Laundry Room | 500 | Robust Shelving | Not Started
4 | Yard | 40000 | Playground & Fence | In Progress | Southside Baptist/FBC Branson
4 | Electrical Service | 10000 | Upgrade from 200A to 400A Service | Not Started | BH Power
4 | Grounds | 0 | Cut Down Trees along east side of parking lot | Not Started
4 | Carport | 25 | Haul Garbage to Dump | Not Started | Brad Green
5 | Baptistry - West Wall | - | Emergency Exit Plan (Door or Window) | Not Started
5 | Parking Lot | 50000 | Paving (Wait on Building Project in 2028) | Not Started
5 | Sound Booth - Fellowship | 2000 | Build / Wire Sound Booth | Not Started
| Total: | 170765
Priority |  |  |  |  | Contacts
1 - Required / Highly Desired |  |  |  |  | Andy Daniel
2 - Required Function |  |  |  |  | 417-824-7177
3 - Needed Function |  |  |  |  | Brad Green
4 - Needed, but not Pressing |  |  |  |  | 605-858-5749
5 - Desired
Notes
Items without a cost associated are either manpower specific, or require quotes

## Completed
Mercy Gate Church Box Elder - Completed Project List
Date of Completion | Priority | Location | Project | Estimated Cost | Actual Cost | Manhours | Notes | Point of Contact
2023-01-22 | 1 | Entire Building | Electrical at Kids Height | 100 | 26 | 5 |  | Canyon Shearer
2023-01-22 | 2 | Entry Hall | Verify Breakers Properly Terminated | 100 | - | 0.5 |  | Canyon Shearer
2023-01-22 | 2 | Key Inventory | Label / Inventory Keys | - | - | 2 |  | Kris Zeronas
2023-01-27 | 2 | Worship Hall | Replace Lights | 500 | 500 | 3 |  | Andy Daniel
2023-01-27 | 1 | Walkway | Remove Decrepit Flower Beds | - | - | 35 |  | Kris Zeronas
2023-02-01 | 1 | Shower Block | Repair Water Heater | 150 | 950 | 16 | Water Heater Replaced | Brad Green
2023-02-01 | 1 | Fellowship Hall | Rebuild Toilet | 25 | 25 | 1 |  | Brad Green
2023-02-02 | 1 | Internet | Internet / WiFi to Building | - | - | 0.5 |  | Andy Daniel
2023-02-04 | 1 | Nursery | Deep Clean | - | - | 2 |  | Tina Shearer
2023-02-04 | 1 | Nursery | Changing Table | - | - | 2 |  | Kodi McKenna
2023-02-04 | 1 | Women's WC | Changing Table | - | - | 2 |  | Kodi McKenna
2023-02-04 | 1 | Trash | Take Debri to Transfer Station | 350 | 216 | 5 | 6 Tons | Andy Daniel
2023-02-05 | 1 | Worship Hall | Setup Sound | - | - | 16 |  | Craig Walsh
2023-02-05 | 1 | Baptistry | Cover Window and Mount Cross | 100 | 77 | 4 |  | Canyon Shearer
2023-02-05 | 1 | Children's Church | Floor | 200 | 160 | 5 |  | Tabby / Tina
2023-02-08 | 1 | Kids Check In | GFCI - 20A | 25 | 25 | 1 |  | Canyon Shearer
2023-02-08 | 2 | Exterior Lighting | Replace Soffit Lights / Cross Lights | 500 | 200 | 6 | Switched at Panel | Canyon / Kris
2023-02-08 | 2 | Exterior Lighting | Replace Cross Light | 50 | 80 | 1 | Auto-Switched in Baptistry Crawl Space | Canyon Shearer
2023-02-11 | 1 | Bathrooms | Replace Signs | 5 | 5 | 1 |  | Canyon Shearer
2023-02-11 | 1 | Childrens Area | Fix Accoustics | 200 | 350 | 3 | Square Padding | Tabby / Tina
2023-02-11 | 3 | Laundry Room | P-Trap for Washer | 100 | 122 | 5 |  | Brad Green
2023-02-12 | 1 | Foyer | Exit Light | 100 | 59 | 2 |  | Canyon Shearer
2023-02-13 | 2 | Exterior | Signs | 1000 | 850 | 1 |  | Andy Daniel
2023-02-13 | 1 | Worship Hall | Mount Camera | 10 | - | 4 |  | Kris Zeronas
2023-02-17 | 1 | Worship Hall | Baptistry Cover Paint / Stain | 25 | 5 | 2 |  | Canyon Shearer
2023-02-17 | 1 | Sinks | Water Filtration | 250 | 340 | 5 |  | Brad Green
2023-02-18 | 1 | HVAC | Replace Filters | 100 | 20 | 1 |  | Brad / Canyon
2023-02-18 | 1 | Worship Hall | Mount Confidence TV Monitor | - | 8 | 3 |  | Canyon / Kris
2023-02-18 | 1 | Worship Hall | Mount Visio TV Screens | - | - | 3 |  | Canyon / Kris
2023-02-18 | 2 | Internet | WiFi Repeaters | 450 | 200 | 1 | Cat 5 Preferred, Working on WiFi | Craig Walsh
2023-02-19 | 1 | Worship Hall | WiFi Signs | 5 | 5 | 1 |  | Canyon Shearer
2023-02-20 | 2 | Exterior - SW Facia | Outlet for Exterior Camera | 25 | 25 | 0.5 | Circuit 9 | Canyon Shearer
2023-02-20 | 2 | Exterior - SW Facia | Exterior Camera | 129 | 129 | 0.5 |  | Craig Walsh
2023-02-20 | 2 | Exterior | South Address Number | - | 4 | 0.5 |  | Canyon Shearer
2023-02-24 | 1 | Exterior Doors | Rekey 12 Locks - See Rekey List Tab | 1000 | 550 | 2 |  | Andy Daniel
2023-03-03 | 1 | Entire Building | Security System | 1000 | 1020 | 2 |  | Andy Daniel
2023-03-04 | 2 | NorthEast Kids Room | Replaced Worn Out Outlet | - | 3 | 1 |  | Canyon Shearer
2023-03-04 | 2 | Kids Bathroom | Motion Sensior | 25 | 21 | 1 |  | Canyon Shearer
2023-03-05 | 1 | Fellowship Hall | Baby Gate | 100 | 100 | 0.5 |  | Kris Zeronas
2023-03-05 | 1 | Sound Booth | New Computer Monitors / TVs | 300 | 280 | 3 |  | Andy Daniel
2023-03-09 | 3 | Worship Hall | Remove Fans | 300 | - | 3 | Mounts/Electrical Removed for Safety | Canyon Shearer
2023-03-14 | 2 | Fellowship Hall | Knockout Walls | 5000 | - | 160 |  | South Gate
2023-03-14 | 2 | Children's Church | Paint | - | - | 160 |  | South Gate
2023-03-14 | 2 | West Bedrooms | Troubleshoot Electrical | - | 25 | 4 | Bad Breaker | South Gate
2023-03-14 | 3 | Exterior East Downspot | Remove Birds Nest | - | - | 0.5 |  | Canyon Shearer
2023-03-14 | 4 | Worship Hall | Evaluate Burned Trusses in South Ceiling | - | - | 1 | One small roof sag, ceiling in good shape | South Gate
2023-03-16 | 3 | HVAC - Worship Hall | Base Board Heating Cover Leveling - East Wall | - | - | 2 |  | Canyon Shearer
2023-03-17 | 1 | HVAC | Audit Energy Loss Points | - | - | 3 | Report in PDF | Canyon Shearer
2023-03-17 | 1 | Exterior GFCI for Sign | Replace / Repair GFCI & Wiring | 25 | 25 | 2 | Moved GFCI Inside of Baptistry Crawl Space | Canyon Shearer
2023-03-22 | 1 | Parking Lot | Remove Construction Debris | 150 | 90 | 8 |  | Andy / Canyon / Devin
2023-03-29 | 3 | HVAC - Worship Hall | Base Board Heating Cover Leveling - West Wall | 25 | - | 5 |  | Canyon Shearer
2023-04-01 | 4 | Laundry Room | Washer and Dryer | 2000 | - | 2 | Donated by Love INC | Love INC / Andy / Devin
2023-04-01 | 5 | HVAC - Fellowship Hall | Base Board Cover Replacement | - | - | 2 |  | Canyon Shearer
2023-04-05 | 1 | Parking Lot | Spread Gravel (Wagon Donated) | - | - | 3 |  | Shearer Kids
2023-05-30 | 2 | Parking Lot | Remove Debri and Run Magnet for Nails | 75 | 75 | 2 | High power magnet purchased for church | Canyon Shearer
2023-05-30 | 3 | Bathrooms | New Door Handles | 300 | 150 | 3 |  | Canyon Shearer
2023-05-30 | 3 | HVAC - Attic | Automatic Vent Fans | 500 | 350 | 6 |  | Canyon Shearer
2023-05-30 | 4 | Parking Lot | Remove Stumps in Parking Lot Island | 250 | - | 2 |  | Canyon Shearer
2023-06-05 | 1 | Exterior Doors | Door Stops | 24 | 24 | 3 |  | Hernando Team
2023-06-05 | 2 | Exterior - SW Facia | Troubleshoot Lights | 50 | 25 | 20 |  | Hernando Team / C Shearer
2023-06-05 | 3 | Exterior West Facia | Remove Birds Nest, Fix Gap | 50 | - | 0.5 |  | Hernando Team
2023-06-05 | 4 | Landscaping | Beautification | 500 | 500 | 6 |  | Hernando Team
2023-06-06 | 1 | Childrens Area | Mount Shelving - Shelves are in Storage Room | 8 | 8 | 10 |  | Canyon Shearer
2023-06-07 | 4 | Electrical Overhaul | Upgrade Panels | 2500 | 2500 | 12 |  | Hernando Team
2023-06-13 | 2 | Fellowship Hall | Level Floor | 500 | 500 | 15 | New subfloor laid | South Haven
2023-06-14 | 2 | Fellowship Hall | New Carpet or LVP - $5000 Grant from DBC | 7500 | 7500 | 45 | Paid for by DBC Grant | South Haven
2023-06-15 | 3 | Fellowship Hall | New Paint | 500 | 500 | 10 |  | South Haven
2023-06-15 | 1 | Hall | Electrical for Camera / Exit Light | 50 | 50 | 7 |  | Canyon Shearer
2023-06-15 | 2 | Worship Hall | Rebuild Running Toilet | 25 | 25 | 1.5 |  | Brad Green
2023-06-17 | 2 | Kitchen | Oven Ventilation - See Kitchen Tab | 500 | 250 | 20 |  | South Haven
2023-06-17 | 2 | Parking Lot | Remove / Store Cinder Blocks | - | - | 4 |  | Mercy Gate Rapid City
2023-06-17 | 4 | Kitchen | Renovate - Note 1 | 22750 | 23000 | 400 |  | South Haven
2023-06-20 | 2 | Kitchen | Dishwasher Connect | 100 | 100 | 5 |  | South Haven / B Green
2023-06-20 | 2 | Kitchen | Garbage Disposal Connect | 100 | 100 | 4 |  | South Haven / C Shearer
2023-07-01 | 1 | WiFi | Cat 5 Hardwired WiFi Repeaters | 350 | 350 | 4 |  | Devin Long / Andy Daniel
2023-07-01 | 2 | Entire Building | Electrical above Kids Height | 500 | 300 | 25 |  | Canyon / South Gate
2023-07-13 | 2 | Fellowship Hall Ramp | Refurbish | 500 | 500 | 64 |  | Longview Heights
2023-10-01 | 2 | Coffee Corner | Permanent Serving Bar | 1000 | 1000 | 40 |  | FBC Branson, Missouri
2023-10-01 | 2 | Kitchen | Connect / Repair Ice Makers | 50 | 50 | 3 |  | Brad Green
2023-10-01 | 2 | Kitchen | Island Electrical | 50 | 50 | 2.5 |  | Canyon Shearer
2023-10-01 | 2 | Kitchen | Warming Tray Electrical - Wires in Place | 50 | 50 | 2.5 |  | Canyon Shearer
2023-10-01 | 3 | Childrens Area | Label Storage Cabinets | 5 | 5 | 3 |  | Ladies Group
2023-10-01 | 3 | Kitchen Area | Label Storage Cabinets | 5 | 5 | 3 |  | Ladies Group
2023-10-15 | 3 | Trailer Foundation | Shore Up Foundation Under Kitchen | 15000 | - | 40
2024-02-28 | 3 | Fellowship Hall | Label Circuit Breaker Panel | - | - | 3 |  | Shearer Boys
2024-03-02 | 4 | Janitor Closet | Paint / Mount Peg Board / Basic Tools | 100 | 173 | 8 |  | Canyon / Jacob
2024-03-02 | 3 | HVAC - Janitor's Closet | Spray Foam West Outlets/Wall | 20 | 17 | 0.5 |  | Canyon Shearer
| 1 | Fellowship Hall | Handicap Accessible Bathroom |  |  | 40 |  | Chester Baptist, Ackerman Mississippi
| 2 | Fellowship Hall | Replace Siding |  |  | 240 |  | Neshoba Baptist Association, Neshoba County Mississippi
2024-09-10 | 2 | Fellowship Hall | Replace Windows |  |  | 60 |  | Neshoba Baptist Association, Neshoba County Mississippi
| 2 | Entire Building | Paint Exterior of building and garden shed |  |  | 240 |  | Neshoba Baptist Association, Neshoba County Mississippi
| 2 | Sound Booth-Worship Hall | Expand/Upgrade Sound Booth |  |  | 40 |  | Ridgecrest Baptist, Springfield Missouri
2024-09-20 | 5 | 6-8 Yr Old Room | Replace Lights | 150 | 0 | 2 |  | Southside Baptist, Alma Arkansas
2024-09-20 |  | 4-6 Yr Old Room | Replace Lights |  | 0 | 2 |  | Southside Baptist, Alma Arkansas
2024-09-20 |  | Nursery | Replace Lights |  | 0 | 2 |  | Southside Baptist, Alma Arkansas
2024-09-20 |  | Nursery | Mount TV |  | 0 | 2 |  | Southside Baptist, Alma Arkansas
2025-02-21 | 3 | Fellowship Hall | New Locking Doorknobs | 100 | 40 | 0.5 |  | Brad Green
2025-03-01 | 3 | Worship Hall | Install Second Camera for Livestream |  | 50 | 4 |  | Tim Ayers/Josh Jenkins
2025-03-01 | 3 | Worship Hall | Replace VGA Cables with HDMI for Stage Screens |  | 50 | 4 |  | Tim Ayers/Josh Jenkins
|  |  |  | Total | 44792 | 1916.5

## Big Purchases
Mercy Gate Church - Box Elder Future Big Purchases
Item | Location | Cost | Notes | Progress | Point of Contact
Washer | Laundy Room | - | Electric | Complete | LoveINC
Dryer | Laundy Room | - | Electric | Complete | LoveINC
Chest Freezer | Kitchen | 1000 | Donations from OneHeart / Safeway | Complete | Andy Daniel
Keyboard | Worship Hall | 871 | - | Complete | Andy Daniel
Lawnmower | Shed | 5000 | Zero Turn | Complete | Andy / Brad
Snowplow 4 wheeler | Shed | 10000 | - | Complete | Andy
Siding | Fellowship Hall | 52435 | Completed by Mission Team | Complete
Pressure Washer | Shed | 500 | - | Not Started
Shredder - HD | Office | 300 | - | Not Started
Confidence Monitor | Worship Hall | 300 | Current Monitor is Dangerously Heavy | Not Started
Counseling Package | Foyer | 1000 | https://newgrowthpress.com/minibooks/minibook-packages/2022-30-title-minibook-counseling-resource-package/ | Not Started
Playground | Front | 40000 | - | Not Started
Foundation Repair | South Worship Hall | 31000 | Baptistry | Not Started
Light Controller | Worship Hall | 1000 | - | Not Started
Cameras | Worship Hall | 1500 | - | Not Started

## Paint Tracker
Mercy Gate Church Box Elder Paint Tracker
Room | Paint Color | Paint Name | Paint Code | Paint Type | Manufacturer
Foyer | Red | Habanero Chile | 7589 | Architectural Latex - Semi-Gloss | Sherwin Williams
Children's Area | Red | Habanero Chile | 7589 | Architectural Latex - Semi-Gloss | Sherwin Williams
Children's Area | White | Snowbound | 7004 | Architectural Latex - Semi-Gloss | Sherwin Williams
Fellowship Hall | White | Snowbound | 7004 | Architectural Latex - Semi-Gloss | Sherwin Williams
Kitchen | White | Snowbound | 7004 | Architectural Latex - Semi-Gloss | Sherwin Williams

## Consumables Tracker
Mercy Gate Church - Box Elder Consumable Tracker
Consumable | Type | Location | Cost | Replaced | Due | Notes
Water Filter | Sediment/Carbon | Worship Hall | 50 | 2023-02-01 | 2024-02-01
Water Filter | Sediment/Carbon | Children's Area | 50 | 2023-02-01 | 2024-02-01
Water Filter | Sediment/Carbon | Fellowship Hall | 50 | 2023-02-01 | 2024-02-01
Air Filter | HVAC - Air Handler | Worship Hall | 10 | 2024-02-14 | 2024-08-18
Air Filter | HVAC - Air Handler | Children's Area | 10 | 2024-02-14 | 2024-08-18
AA Battery | Boiler Thermostat | Worship Hall | 5 | 2023-02-17 | 2025-02-01
AA Battery | Boiler Thermostat | Fellowship Hall | 5 | 2023-02-01 | 2025-02-01
AA Battery | HVAC Thermostat | Children's Area | 5 | ? | -
AA Battery | HVAC Thermostat | Worship Hall | 5 | ? | -
Roof | Metal | Worship Hall | 20000 | 2003-01-01 | 2043-01-01 | 40 yr estimate
Roof | Metal | Fellowship Hall | 20000 | 2020-01-01 | 2065-01-01 | 40 yr estimate

## Door Key List
Mercy Gate Church Box Elder - Door Key List
# | Door | Location | Interior/Exterior | Key | Notes
1 | Main Entry | East Red Door | Exterior | Main
2 | Worship Hall 1 | East / South | Exterior | Main
3 | Worship Hall 2 | East / South | Exterior | Main
4 | Breezeway | East / Middle | Exterior | Main
5 | Fellowship Hall | East / North | Exterior | Main
6 | Church Office | Main Hall | Interior | Main
7 | Pastors Office | Off Main Hall | Interior | Pastors
8 | Children's Church South | Off Main Hall | Interior | Main
9 | Storage Shed | North Side | Exterior | Main
10 | Storage Shed Garage | East Side of Shed | Exterior | Garage
11 | Worship Hall Storage | West | Interior | Main
12 | Worship Hall Storage | East | Interior | Main
13 | Children's Church North | Off Breezeway | Interior | Main
14 | Garden Shed | Parking Lot | Exterior | Shed
15 | Janitor's Closet | Off Breezeway | Interior | Main
16 | Apartment | Fellowship Hall | Interior | Apt | Spare in Pastor's Office Keybox
17 | Front Boiler Room | Main Entry | Interior | Main
18 | Back Boiler Room | Fellowship Hall | Interior | Main
19 | Pantry | Fellowship Hall | Interior | Main
Mercy Gate Church Box Elder - Doors Need Rekeyed
# | Door | Location | Interior/Exterior | Key | Notes

## Kitchen
Kitchen Refurbish - Completed
Step | Project | Cost (Est) | Notes | Progress
1 | Plan Kitchen Layout | - |  | Complete
2 | Demo Existing Kitchen | 150 | Donated Oven to Love INC | Complete
3 | Upgrade Electrical | 350 | GFCIs / Garbage Disposal / Nice Lighting | Complete
3 | Upgrade Plumbing | 250 |  | Complete
3 | Upgrade Natural Gas | 2000 |  | Complete
4 | Replace Window | 1000 |  | Complete
4 | Oven Ventilation | 500 |  | Complete
5 | Drywall / Paint | 2500 |  | Complete
6 | Floor | 2500 |  | Complete
7 | Cabinets | 3000 |  | Complete
8 | Countertop | 4500 |  | Complete
9 | Oven | 5000 |  | Complete
11 | Dishwasher | 1000 |  | Complete
| Total | 22750 | Planned/Worked by Ridgecrest and South Haven