## Slide 1: Congregational Update Session
Morning Star Baptist Church
Pastoral Search Committee
June 27, 2026
“Together We Can, Together We Will”

## Slide 2
Meeting Structure
Congregational Update Session — June 27, 2026
Information Session
Review
Time Efficiency
Q&A

## Slide 3
Agenda
Congregational Update Session — June 27, 2026
Review
PSC Process
Project Plan
Q&A

## Slide 4
Review
Congregational Update Session — June 27, 2026
May 15th - Info Session
Surveys
Information included in handout

## Slide 5
The Process
Application /Screening
Scheduling Interviews
Interviews:
1st round
3rd & 4th
Round
2nd round
Initial Application Screening
  Review all applications to ensure candidates meet the minimum required qualifications effectively.
Detailed Interviews
  1st round involves in-depth interviews focusing on pastoral experience and personal character evaluation.
Initial Interviews
  1st round involves WHO and WHY.
  Values Alignment Check
  Assess candidates to verify their alignment with the church’s core values and community needs.
Comprehensive Review
  The committee carefully analyzes all collected data to evaluate each candidate’s suitability and potential.

## Slide 6
Project Plan

## Slide 7
Our Pastoral Search
A Process Rooted in Prayer, Transparency & Trust
To be completed in early 2027
Presented to the Congregation by the Pastoral Search Committee
Notes: Welcome and open with prayer. This presentation walks the congregation through each phase of the pastoral search. Emphasize that every member's voice matters — especially in the surveys and the final vote.

## Slide 8
How the Search Unfolds
Four Spirit-led phases — from listening to welcoming our new pastor
01
Listen
Jun–Aug 2026
Surveys,
information sessions, and online page
›
02
Discern
Aug–Nov 2026
PSC reviews candidates, and interviews are conducted
›
03
Choose
Nov–Dec 2026
Finalist presented, pre-vote briefing, members vote
›
04
Welcome
Dec 2026–Jan 2027
Call accepted and a new chapter begins
= Pivot point — if the process needs more time, we pause here and keep the congregation informed
Notes: Walk through each phase briefly. Emphasize that this is not a rushed process — discernment takes time. The clock symbols on the next slides show where we may intentionally pause if God's leading requires more time.

## Slide 9
Phases 1 & 2 — Listen & Discern
June – November 2026
Jun 8
Application portal opens
Jun 27
Congregational Info Session #2
Aug 8
Applications Portal Closes
PIVOT: If too few qualified candidates apply, PSC may extend the deadline by 2–4 weeks and notify the congregation.
Sep 19
Congregational Info Session #3
Aug 24–Oct 19
Candidate interviews (rounds 1, 2 & 3)
PIVOT: If no candidate meets the standard after round 2, PSC may reopen the search or extend the interview process. Congregation will be notified at the Sept. Info session.
Notes: Key point: we are committed to quality over speed. The two pivot points on this slide (application deadline and interviews) are moments where the PSC has permission to pause and extend — always with full transparency to the congregation.

## Slide 10
Phases 3 & 4 — Choose & Welcome
November 2026 – January 2027
Nov 8–15
Congregational Survey #2
Nov 21
Pre-vote information Session
.
Dec 5
PSC Chair presents a recommendation for members’ vote
Dec 19
THE CHURCH VOTE -- Every member casts their vote. Pivot
Dec 21–31
Offer made and call accepted
Notes: The church vote is our most sacred congregational act in this process. Remind members that a 2/3 majority reflects broad unity — not a simple majority. If we don't reach that threshold, the PSC will not rush. We will seek God together.

## Slide 11
Understanding Our Pivot Points
What happens if the process takes longer than planned?
1
Applications fall short
WHEN
After Aug 8 deadline
WHAT WE DO
PSC extends portal 2–4 weeks & widens outreach network
OUR COMMITMENT TO YOU
Pivot plan discussed at the Sept information session
and
2
No candidate clears interviews
WHEN
After round 2 or 3
WHAT WE DO
PSC may reopen search & widens outreach network
OUR COMMITMENT TO YOU
Full update shared with congregation within 2 weeks
3
Vote does not reach 2/3
WHEN
After Dec 19 vote
WHAT WE DO
PSC returns to discernment; congregation called to prayer
OUR COMMITMENT TO YOU
New timeline shared within 30 days
In every scenario, we will be transparent, prayerful, and patient — trusting God's timing above our own.
Notes: These pivot points are not failures — they are built-in moments of Spirit-led flexibility. Share that the PSC has discussed each scenario and is committed to never rushing the process at the expense of God's leading.

## Slide 12
Your Role
Matters
This search belongs
to all of us.
The Lord will guide
continually…
— Isaiah 58:11
How You Can Participate
🙏
Pray daily
📋
Complete every survey
📅
Attend information sessions
🗳️
Vote on December 19
💬
Ask questions and visit the PSC webpage
Notes: Close in prayer. Remind the congregation that their participation in surveys and the vote is an act of worship and stewardship. The PSC is honored to serve in this sacred task.

## Slide 13
Q&A

## Slide 14: Congregational Update Session
Morning Star Baptist Church
Pastoral Search Committee
June 27, 2026
“Together We Can, Together We Will”