Event Planning Work Sheet /Checklist / Evaluation

Lead Times: (C) Conferences, (W) Workshops, (O) Other

| STAGE I: EVENT APPROVAL |  |  |  |  |  | DONE |
| --- | --- | --- | --- | --- | --- | --- |
| Lead Time: (C) 6-12 months* (W) 6 months (O) 3-4 months |  |  |  |  |  |  |
| - Submit appropriate forms to Pastoral/Elders for Event (Building Usage, Voucher, etc.) |  |  |  |  |  |  |
| - Upon event approval, agree upon physical arrangements (rooms & set-up) and submit appropriate form for securing rooms |  |  |  |  |  |  |
| - Select and invite guest speakers |  |  |  |  |  |  |
| - Schedule a meeting with the Pastoral/Executive Coordinator for discussion (if needed) |  |  |  |  |  |  |
| MEETING DATE: |  |  |  |  |  |  |
| STAGE II: INITIAL CONTACT WITH PARTNER MINISTRY(S) |  |  |  |  |  |  |
| Lead Time: (C) 6 months |  |  | (W) 4-6 months* | (O) 3 months |  |  |
| - Confirm dates and budget for event |  |  |  |  |  |  |
| - Clarify needs: |  |  |  |  |  |  |
| Administrative |  |  |  |  |  |  |
| Audio |  |  |  |  |  |  |
| Musicians |  |  |  |  |  |  |
| Hospitality |  |  |  |  |  |  |
| Finance |  |  |  |  |  |  |
| Maintenance |  |  |  |  |  |  |
| Exaltation Team |  |  |  |  |  |  |
| Security |  |  |  |  |  |  |
| Transportation |  |  |  |  |  |  |
| Video |  |  |  |  |  |  |
| Other (please list) |  |  |  |  |  |  |
| Schedule meeting with all involved Ministry Leaders (if needed) |  |  |  |  |  |  |
| Prepare assignments/engage volunteers |  |  |  |  |  |  |
| Submit request forms for Communications/ Media /Graphics and Audio/Video Team to elc@emerginglifechurch.org |  |  |  |  |  |  |
| Schedule appointment with Communications/ Media /Graphics and Audio/Video Team (if needed) |  |  |  |  |  |  |
| MEETING DATES: |  |  |  |  |  |  |
| Audio/Visual |  |  |  |  |  |  |
| Communications |  |  |  |  |  |  |
| Others |  |  |  |  |  |  |

Event Planning Work Sheet /Checklist / Evaluation

| STAGE III: FOLLOW-UP WITH MINISTRY DEPARTMENTS |  |  | DONE |
| --- | --- | --- | --- |
| Lead Time: (C) 3 months (W) 3 months (O) 3 months |  |  |  |
| - Submit appropriate request forms for: |  |  |  |
| Announcements _________________________________ |  |  |  |
| Guest Experience (Hospitality) |  |  |  |
| Culinary |  |  |  |
| Registration Set-up |  |  |  |
| - Schedule follow-up meeting with ministry leaders and ministry participants |  |  |  |
| - Send follow-up letters to guests/speakers participating |  |  |  |
| - Arrange for announcements via radio or external entities |  |  |  |
| - Request Volunteers for specific areas |  |  |  |
| Note: Advance requisitions must be submitted (10) days in advance. |  |  |  |
| STAGE IV: PUBLICITY & FOLLOW-UP |  |  |  |
| Lead Time: (C) 2-3 months (W) 2-3 months (O) 2-3 months |  |  |  |
| - Send out mailings to individuals, churches, or organizations |  |  |  |
| - Begin Announcements and Registration |  |  |  |
| - Hand out information after services |  |  |  |
| - Follow-up meeting with Ministry Team Leaders regarding responsibilities |  |  |  |
| - Assign other responsibilities as needed, i.e.: Speaker Host. Program Host, |  |  |  |
| - Follow-up with assignments for volunteers |  |  |  |
| - Schedule final meeting with Ministry Team Leaders, Volunteers, Hosts, etc. |  |  |  |
| STAGE V: FINAL FOLLOW-UP |  |  |  |
| Lead Time: (C) 1 month (W) 1 month* (O) 2-3 weeks |  |  |  |
| - Schedule meeting with ministry team leaders, ministry participants, volunteers, host, etc. |  |  |  |
| - Send final letters to speakers reiterating pertinent info regarding their participation in the conference, i.e. speaking schedule, assigned host, contact numbers, hotel & flight iterate, etc. |  |  |  |
| *Applicable for out of town guests only. Final letters may be mailed at 2-3 weeks for in-town guest speakers. |  |  |  |
| FINAL FOLLOW-UP MEETING: |  |  |  |

Event Planning Work Sheet /Checklist / Evaluation

| STAGE VI: PREPARATION |  |  |  |  | DONE |
| --- | --- | --- | --- | --- | --- |
| Lead Time: 1-2 weeks |  |  |  |  |  |
| 1.) FINANCES |  |  |  |  |  |
| - Submit Requisitions for all speaker’s offering (10) days in advance of date needed |  |  |  |  |  |
| 2.) SPEAKERS |  |  |  |  |  |
| - Final Hosting Assignments (Include emergency contact #’s) |  |  |  |  |  |
| - Hotel Accommodations Info |  |  |  |  |  |
| - Transportation arrangements for Speakers |  |  |  |  |  |
| - Review Itinerary |  |  |  |  |  |
| OTHER PREPARATION |  |  |  |  |  |
| Lead Time: 1-2 days prior to event |  |  |  |  |  |
| 1.) FACILITY (Building usage request and room set up forms should be submitted 4 wks in advance) |  |  |  |  |  |
| 2.) EQUIPMENT (Equipment request form should be submitted 4 weeks in advance) |  |  |  |  |  |
| - Audio-Visual needs (i.e. sound system, projector, screen, microphones, extension cords, etc) |  |  |  |  |  |
| - Podium |  |  |  |  |  |
| - Chairs (#___________) |  |  |  |  |  |
| - Tables (#___________) |  |  |  |  |  |
| - Display and registration area with table and chairs (# tables________ #chairs __________) |  |  |  |  |  |
| - Easel / Flip Chart / Markers |  |  |  |  |  |
| - Registration forms |  |  |  |  |  |
| - Tape |  |  |  |  |  |
| - Money Box and change |  |  |  |  |  |
| - Rented equipment will be provided by the following: |  |  |  |  |  |
| - Company / Person____________________________ |  |  |  |  |  |
| - Phone # ____________________________________ |  |  |  |  |  |
| 3.) FOOD |  |  |  |  |  |
| - Tables and chairs for meal |  |  |  |  |  |
| - Coffee, hot water, tea, cream & sugar, etc. |  |  |  |  |  |
| - Extension Cords |  |  |  |  |  |
| - Trash Containers |  |  |  |  |  |
| - Table Decorations |  |  |  |  |  |
| - Dishes, napkins, etc. |  |  |  |  |  |
| - Adequate volunteers for serving |  |  |  |  |  |
| - Clean-up |  |  |  |  |  |

Event Planning Work Sheet /Checklist / Evaluation

| 4.) PROGRAM PREPARATION | DONE |
| --- | --- |
| - Host appointed |  |
| - Agenda planned |  |
| - Sound and equipment set up and checked |  |
| - Persons involved informed of their responsibility |  |
| - Pre-service briefing & Prayer (15 minutes prior to start time) |  |
| STAGE V: EVENT CLOSURE |  |
| - Event location cleaned and restored to proper order |  |
| - Evaluation(s) completed |  |
| - Special commitments and promises followed up |  |
| - Requisitions for reimbursements submitted with all receipts (if applicable) post |  |

POST EVENT EVALUATION

How did we meet our goals/objectives? If they were not met, why not?

Did we meet our budgetary goals?

Did we have enough volunteers for the event?

Did we have adequate advertising/public relations for the event? How could we have made this better?

Would we execute this or a similar event in the future? If so, suggestions for improvement.